## GMV Max Tracker
Date | Campaign Type | Campaign Name | Product IDs / SKUs | Target ROI (e.g., 2.0 = 200%) | Optimization Mode (Max Delivery / Target ROI) | Daily Budget (IDR) | Spend (IDR) | Gross Merchandise Value - GMV (IDR) | Orders | Average Order Value - AOV (IDR) | Click Through Rate - CTR (%) | Conversion Rate - CVR (%) | Creative Count | Live Hosts / KOL | Voucher Type (Xtra / Seller / Platform) | Free Shipping Subsidy (IDR) | Commission Rate (%) | Platform Fee (IDR) | Net Revenue After Fees (IDR) | ROI (GMV / Spend) | Notes
2025-11-01 | Product GMV Max | 11.11 Warm-Up Bundle | SKU-123, SKU-456 | 2.5 | Target ROI | 3000000 | 2500000 | 7000000 | 180 | 38888.8889 |  |  | 8 | Creator A | Seller | 200000 | 5.5 | 385000 | 6415000 | 2.8 | Baseline target, scale if ROI>=target for 2 days

## 11.11 Timeline
Day Offset | Date | Workstream | Task | Owner | Status | Notes
D-30 | 2025-10-12 | Inventory & Bundle | Lock forecast, secure safety stock, define 11.11 bundles and AOV target |  | Not started
D-21 | 2025-10-21 | Catalog & PDP | Optimize titles, images, variant mapping, ensure Shop Tab eligibility |  | Not started
D-18 | 2025-10-24 | Data & Pixel | Verify Events API, catalog mapping, test postback to Ads Manager |  | Not started
D-14 | 2025-10-28 | Creative Sprint | Plan 10-20 fresh ads, UGC hooks, price tests, CTA variants |  | Not started
D-10 | 2025-11-01 | KOL & LIVE | Lock hosts, scripts, affiliate rates, incentive mechanics |  | Not started
D-7 | 2025-11-04 | Warm-up | Start Max Delivery runs with small budget, gather learnings |  | Not started
D-5 | 2025-11-06 | ROI Target | Set target ROI based on last 7 days, define min and expected spend ranges |  | Not started
D-3 | 2025-11-08 | Voucher & Shipping | Program platform Xtra voucher, seller vouchers, free shipping caps |  | Not started
D-1 | 2025-11-10 | Dry Run | Full system test, stock reservation, schedule posts and LIVE slots |  | Not started
D+0 | 2025-11-11 | 11.11 Day | Switch to Target ROI after ramp, monitor spend and inventory every 2 hours |  | Not started
D+1 | 2025-11-12 | D+1 Post-Game | Retarget non-buyers, spin best sellers into evergreen, consolidate reviews |  | Not started
D+3 | 2025-11-14 | D+3 Finance | Reconcile fees, commissions, ROI, finalize learning agenda |  | Not started