## Overview
Phase | Dates | Objective | Primary KPI | Secondary KPI | Platforms | Budget Split % | Notes
Pre‑Peak | Nov 1–Nov 20, 2025 | Warm intent, build remarketing pools, fix data quality | Add‑to‑Cart rate | List growth, Creative CTR | Meta, Google, TikTok | Meta 35, Google 45, TikTok 20 | Turn on lift tests early
Cyber Week | Nov 27–Dec 1, 2025 | Maximize profitable scale across platforms | Revenue, ROAS | MER, Orders per hour | Meta, Google, TikTok | Meta 40, Google 40, TikTok 20 | Increase caps with staged budgets
Peak | Dec 2–Dec 22, 2025 | Sustain volume with fresh creatives and offers | ROAS with guardrails | Click to purchase rate | Meta, Google, TikTok | Meta 35, Google 45, TikTok 20 | Refresh creatives weekly
Late Season | Dec 23–Dec 31, 2025 | Gift cards and fast shipping, local pick up | Checkout completion rate | Store visits, Gift card GMV | Meta, Google | Meta 30, Google 70 | Shift to local inventory ads
Q5 | Jan 1–Jan 31, 2026 | Harvest warmed audiences at lower CPMs | CAC, New customer rate | Email sign ups | Meta, TikTok, Google | Meta 40, TikTok 30, Google 30 | Test subscriptions and bundles

## Meta
Item | Owner | Status | Due | Notes
ASC structure with Advantage+ Audience only, geo and language gated | Performance |  |  | One ASC for scale, one BAU retargeting set
Upload 10–20 creatives per ASC, use UGC and real people | Creative |  |  | Rotate weekly, 2–3s hooks
Enable Conversions API with deduplication | Data |  |  | Check event match quality
Catalog set with accurate availability and price | Data |  |  | Sync daily
Set staged budgets for BFCM hours | Ops |  |  | Automated rules on ROAS and CPA
Run Conversion Lift test from early November | Measurement |  |  | Define success metrics in advance

## Google
Item | Owner | Status | Due | Notes
Performance Max as core with high quality Merchant Center feed | Performance |  |  | Fix disapprovals before Nov 20
Asset groups mapped by product theme | Creative |  |  | Each with 15 headlines and 4 long headlines
Enable enhanced conversions and first‑party audiences | Data |  |  | Consent mode v2 verified
Budget rules for peak days and shipping cutoffs | Ops |  |  | Shift to gift cards post cutoff
Search brand protection with exact match | Performance |  |  | Layer on value‑based bidding
Run geo holdout or seasonality adjustment tests | Measurement |  |  | Use lift or drafts and experiments

## TikTok
Item | Owner | Status | Due | Notes
Smart+ Catalog with ≥6 creatives to start | Performance |  |  | Add 6+ new creatives weekly
GMV Max campaign for BFCM and December | Performance |  |  | Ensure 49+ creatives in campaign
Daily LIVE cadence during Cyber Week | Ops |  |  | 1–2 sessions per day, 3 hours each
Use Interactive Add‑Ons for urgency | Creative |  |  | Countdowns, flash sale stickers
Post Purchase Survey enabled | Measurement |  |  | Attribute halo to TikTok Shop vs Web
GA4 linked inside TikTok Attribution Analytics | Data |  |  | Bridge reporting gaps

## Creative Matrix
Hook | Format | Message | Use For | Notes
Problem to payoff in first 2s | 9:16 video, Reels, Shorts | Show person using product, speak benefits, then demo | Top and Mid funnel
Side‑by‑side before after | 9:16 video | Visual transformation with proof element | Mid funnel
Gift guide with price tiers | Carousel, Collection Ad | Under $25, $50, $100, link to bundles | Top funnel
Unboxing with voiceover and captions | UGC video | Human hands visible, brand neutral background | Mid to Bottom funnel
Creator testimonial with social proof overlay | UGC video | Show star ratings and review count | Bottom funnel

## Measurement
Item | Status | Notes
Meta CAPI dedupe passing | Yes/No
GA4 purchase value verified | Yes/No
TikTok PPS live | Yes/No
Meta Conversion Lift running | Yes/No
Geo holdout defined | Yes/No
UTM builder enforced | Yes/No
Attribution readouts cadence | Daily/Weekly

## Daily Ops
Date | Platform | Spend | Revenue | Orders | ROAS | MER | CTR | CVR | CPM | CPC | Notes

## UTM Builder
Field | Example
utm_source | meta¦google¦tiktok
utm_medium | paid_social¦cpc¦shop
utm_campaign | hs25_{platform}_{theme}_{aud}
utm_content | cre_{hook}_{format}
utm_term | keyword if search

## QA Preflight
Check | Status
Pixel firing on purchase and add_to_cart
All landing pages pass Core Web Vitals
Shipping cutoff messaging up to date
Promo codes tested in cart
Policy and consent banners working in EU