## Checklist
Workstream | Task | Owner | Due date | Status | Notes
Change 1: Messenger Inbox Deprecation (Nov 11, 2025) | Export a placements breakdown for last 30 days to estimate spend share from Messenger Inbox | Paid Media Lead | 2025-11-08 | Not started | Ads Manager > Reports > Breakdown by placement
Change 1: Messenger Inbox Deprecation (Nov 11, 2025) | Pause any ad sets that explicitly include Messenger Inbox in Manual Placements | Media Buyer | 2025-11-08 | Not started | Switch to Advantage+ placements or remove Messenger Inbox
Change 1: Messenger Inbox Deprecation (Nov 11, 2025) | Update Click-to-Message campaigns, point entry to IG DM, Messenger Chats via Feed or Stories, or WhatsApp if applicable | CRM/CS Lead | 2025-11-08 | Not started | Check destination and entry points
Change 1: Messenger Inbox Deprecation (Nov 11, 2025) | Reallocate budget to top performing placements after removal, set 72h guardrails | Paid Media Lead | 2025-11-08 | Not started | See Spend Guard sheet
Change 2: GA4 Cost Import + UPD (Oct-Nov 2025) | Connect Meta Ads cost import to GA4 | Analytics Lead | 2025-11-08 | Not started | GA4 Admin > Data Import > Cost data > Meta
Change 2: GA4 Cost Import + UPD (Oct-Nov 2025) | Map UTM parameters and check currency/timezone parity | Analytics Lead | 2025-11-08 | Not started | Use UTM Builder sheet
Change 2: GA4 Cost Import + UPD (Oct-Nov 2025) | Build ROAS and CAC views in GA4 Advertising workspace, validate with Ads Manager totals | Analytics Lead | 2025-11-08 | Not started | Use blended reports
Change 2: GA4 Cost Import + UPD (Oct-Nov 2025) | Enable User-Provided Data where lawful, update consent and Customer Match links | Data/Legal | 2025-11-08 | Not started | Follow GA4 UPD guidance
Change 3: Threads Formats + Verification (Q4 2025) | Enable Threads placement with Placement Asset Customization for eligible campaigns | Media Buyer | 2025-11-08 | Not started | Use 4:5 imagery, 1:1 static carousel
Change 3: Threads Formats + Verification (Q4 2025) | Activate IAS/DoubleVerify/Scope3 brand suitability integration where available | Brand Safety | 2025-11-08 | Not started | Coordinate with verification vendor
Change 3: Threads Formats + Verification (Q4 2025) | Create Threads-first creative set, test 4:5 vs 1:1, 6–15s video | Creative Lead | 2025-11-08 | Not started | See Creative Specs sheet
Coming Change: Attribution Window & Data Retention (Jan 12, 2026) | Archive historical Ads Insights exports before retention limits apply, update dashboards | Analytics Lead | 2025-11-08 | Not started | See PPC Land summary and Meta docs

## Spend Guard
Metric | Value | Notes
Daily budget | 100 | Currency in your ad account
Target CPA | 5 | Cost per acquisition goal
Target ROAS | 2 | Revenue / Spend target
Trailing 3-day CPA | 6.2 | Auto pull or enter manually from GA4/Ads
Trailing 3-day ROAS | 1.6 | Auto pull or enter manually from GA4/Ads
Max allowed CPA (Target * 1.2) | 120 | Auto calc
Min allowed ROAS (Target * 0.8) | 4 | Auto calc
Guard Trigger (Yes/No) | YES | YES means pause or reduce 20% until back within guardrails

## UTM Builder
campaign | source | medium | content | term | final_url | utm_string | url_with_utm
nov25_threads_test | meta | paid_social | video_4x5_variantA |  | https://example.com/landing | utm_source=meta&utm_medium=paid_social&utm_campaign=nov25_threads_test&utm_content=video_4x5_variantA&utm_term= | https://example.com/landing?utm_source=meta&utm_medium=paid_social&utm_campaign=nov25_threads_test&utm_content=video_4x5_variantA&utm_term=

## Placement Audit
Campaign | Objective | Manual placements used | Messenger Inbox present | Threads enabled | Asset customization applied | Action by Nov 11
Prospecting_Nov25 | Sales | No | Yes | Yes | Yes | Remove Messenger Inbox
ClickToMessage_Q4 | Leads | Yes | Yes | No | No | Switch to Advantage+ or deselect Messenger Inbox
Retargeting_BlackFriday_Buffer | Sales | No | No | Yes | Yes | Verify Threads creative spec

## Creative Specs
Format | Aspect ratio | Duration / Frames | Recommended text | Notes
Image | 4:5 preferred, 1:1 supported | N/A | Primary up to 125 chars | Use Placement Asset Customization
Video | 4:5, 9:16, 1:1 | 6–15s recommended | Hook in first 2s, captions on | Export captions, include CTA Sticker where available
Carousel | 1:1 static | 2–10 cards | Each card with short value prop | Maintain brand safety guidelines

## ReadMe
Field | Details
About | Template to implement Meta Ads updates Nov 2025, focus on budget protection and Threads testing.
How to Use | Start on the Implementation Checklist, then review Spend Guard thresholds and connect GA4 cost import.
Contact | Team owner fills Status daily during the first 7 days after changes.